## Risk Register
Reference ID | Risk Owner | Title | Risk Description | Inherent Impact | Inherent Probability (Likelihood) | Inherent Risk | Response Type | Response/Control Title | Response/Control Description | Response/Control Mapping | Response/Control Status | Residual Impact | Residual Probability (Likelihood) | Residual Risk | Risk Target
R1 | CISO | Patient Data Breach | Unauthorized access or disclosure of patient health information (PHI) stored in the system. | 9 | 6 | 54 | Reduce | Role-Based Access Control | Role-based access control restricts access to patient data based on user role (admin or staff). | Authentication & Authorization | Implemented | 6 | 3 | 18 | Acceptable
R2 | Development Team | SQL Injection | Malicious input could manipulate database queries and expose or modify sensitive data. | 8 | 5 | 40 | Reduce | ORM & Input Validation | SQLAlchemy ORM and server-side validation prevent execution of raw SQL queries. | Application Security | Implemented | 3 | 2 | 6 | Acceptable
R3 | Development Team | Credential Compromise | User credentials could be compromised if passwords are stored insecurely. | 8 | 5 | 40 | Reduce | Password Hashing | Passwords are hashed using bcrypt before being stored in the database. | Authentication Security | Implemented | 3 | 2 | 6 | Acceptable
R4 | Development Team | Cross-Site Request Forgery (CSRF) | Attackers could force authenticated users to perform unintended actions. | 7 | 5 | 35 | Reduce | CSRF Protection | CSRF tokens are enforced on all state-changing POST requests using Flask-WTF. | Session & Request Security | Implemented | 3 | 2 | 6 | Acceptable
R5 | Development Team | Broken Access Control | Staff users may attempt to access administrative functionality. | 8 | 4 | 32 | Reduce | Server-Side Authorization | Admin-only routes are protected using server-side role validation. | Authorization Controls | Implemented | 3 | 1 | 3 | Acceptable
R6 | DevOps | Information Disclosure via Headers | Server headers may expose framework and version information. | 5 | 5 | 25 | Reduce | Header Hardening | Security headers will be configured in production to reduce information leakage. | HTTP Security | Planned | 3 | 2 | 6 | Acceptable
R7 | IT Operations | Ransomware Attack | On-premise servers could be encrypted due to malware or lack of patching. | 10 | 6 | 60 | Reduce | Patch Management & Backups | Regular patching and isolated backups reduce ransomware impact. | Infrastructure Security | Planned | 6 | 3 | 18 | Acceptable
R8 | Cloud Security Team | Cloud Misconfiguration | Misconfigured cloud services could expose data or services publicly. | 10 | 6 | 60 | Reduce | Cloud Security Baseline | Least-privilege IAM and configuration audits mitigate cloud exposure. | Cloud Security | Planned | 6 | 3 | 18 | Acceptable

## Risk Matrix
Impact
|  | NONE | LOW | MED | HIGH | CRITICAL
Likelihood | RARE |  |  |  |  | Thief stealing a staff’s mobile phone Leading to Account Compromise
UNLIKELY
| COMMON |  | Influencer Recording in-class jokes |  |  | Employees writing down their password on sticky notes and leaving them on their disk, Leading to account compromise.
USUAL
| CERTAIN |  |  | Employees Using their personal devices, downloading sketchy programs